## Slide 1: WASH in Schools
HONDURAS
Rotary Club of Concord, CA

## Slide 2: Program Design
Provide comprehensive WASH infrastructure to 30 schools.
Provide new WASH curriculum
6 Year program with three overlapping Global Grants (Phases) each of 2 year duration.

## Slide 3: How To Perform M & E
International Partner & Host club
Parent Groups
Teachers
Community entities

## Slide 4: Community Involvement
Local Rotary Clubs
Parent Groups
Teachers
Water Committees
Local municipalities
Ministry of Education etc.

## Slide 5: International Partner
3 Annual site visits
Participation in workshops
Interviews with all agencies
Weekly business meeting via Skype
Weekly review of data
Monthly financial review

## Slide 6: HOST CLUB
Liaison with all Community entities
Select/hire Project Manager
Hire Accountant
Hire Community Coordinator
Assign Rotarians to each school
Complete monthly M & E site visit
Train Parent Groups in Data Collection
Facilitate workshops (3) annually
Arrange Teacher Training Workshops

## Slide 7: PARENT GROUPS
Responsible for
Generating funding
Maintaining/repairing WASH infrastructure
Select 4 members for training in data collection (2x2)
Weekly site visits/data collect.
Attend 3 workshops annually

## Slide 9: TEACHERS
Principal is surveyed weekly
Two teachers Female/Male are interviewed weekly
Prepare weekly WASH lesson notes
Teacher WASH Ambassador facilitates data collection.

## Slide 10: Weekly Surveys

## Slide 11: VARIABLES
Are all WASH hardware systems functioning
Breakages
Repairs
Soap available
Toilet paper
Chlorination
Cleaning of bathrooms daily
Teacher supervision of cleaning
Attendance/sick/menstruation
WASH curriculum being taught: frequency/class specifics
Fund collection (Parent Groups)
Etc.

## Slide 14: Instruments
Deliver 18 workshops/focus groups for every community
Monitor & Evaluate project /data collection for 200 weeks.
Monitor & Evaluate Parent Groups for 50 months (Community Coordinator)

## Slide 15: The END
Michael Barrington
Rotary Club of Concord CA, USA
majb7016@gmail.com